## Master Billing Table
# | Date Range | Module / Area | Detailed Scope of Work & Features Implemented | Billable Hours
1 | 08-Apr-2026 to 11-Apr-2026 | Academic Departments Cycle Launch & Examination Schedules | • Coordinated academic department syllabus updates across Computer (be_2019, se_2019, te_2019), ENTC, and MCA (2025-27). • Formatted and optimized faculty portrait photography for AI&DS, Computer, MCA, and Mechanical departments. • Comprehensive FAQ accordion overhauls across AIDS (+320 lines), Comp (+153 lines), Mech (+143 lines), and MCA. • Integrated SPPU Postgraduate Examination Timetables for April/May 2026 session (FY MBA & SY MBA) with dynamic PDF download triggers and mobile link verification. | 10
2 | 12-May-2026 to 16-May-2026 | SDETM 2026 Subdomain Infrastructure, IT Faculty Roster & Student Showcase | • Coordinated with Director IT (Vivek Ganmukhi) and Student Council (Gaurav Nawale) for official conference portal setup (sdetm.indiraicem.ac.in). • Provisioned subdomain on GoDaddy cPanel hosting, structured repository deployments, and coordinated Route53 A-record DNS configuration with central IGI IT team. • Updated Information Technology (IT) department faculty list, designations, qualifications, and profile bios per HOD directive. • Designed, formatted, and integrated homepage hero banner for Preet Mhatre (Google Student Ambassador); authored initial architecture and deployment guide (ICEM KT.md). | 15.5
3 | 18-May-2026 to 21-May-2026 | Research Portal Interactive Showcase (MSME Hackathon 5.0) & National Achievement Banners | • Executed comprehensive research update request from Dean AI & HOD Comp (Dr. Poorna Shankar) via Director IT. • Engineered interactive MSME Hackathon 5.0 timeline showcase (HackathonTimeline.jsx) on /research/ featuring key objectives, multi-stage evaluation processes, funded project rosters, winner lists, and poster modal. • Designed and integrated Team Gemini National Hackathon achievement banner into Homepage HeroSlider with responsive dimensions. | 9.5
4 | 22-May-2026 to 28-May-2026 | SDETM Microsoft CMT Verification, Server Security Audit & Placement Banner Assets | • Resolved critical Microsoft CMT conference crawler block reported by Dr. Saurabh Gupta & Gaurav Nawale. • Created and deployed static verification page cmt.html; configured robots.txt and sitemap.xml to grant full access to Microsoft CMT verification crawlers. • Conducted server-level .htaccess and ModSecurity audit confirming complete absence of anti-bot blocks, securing official CMT domain authorization. • Updated Placed Students Hero Banner for placement season; converted assets to modern AVIF/WebP formats and calibrated slider autoplay timing. | 12
5 | 02-Jun-2026 to 06-Jun-2026 | NBA Department Criteria (Mech/MCA) & Institutional Governance Overhaul | • Received NBA accreditation mandate from Prof. Shubhangi Manwatkar via Director IT; implemented dedicated tab sections for approved Vision, Mission, PEOs, and PSOs on Mechanical Engineering page. • Integrated newly released MCA 2025-2027 curriculum syllabus PDF and updated MCA Program Overview. • Major architecture refactor of OurStaff.jsx (+921 lines): standardized card grid layouts, cleaned staff profile mappings, and fixed mobile alignment. • Overhauled 11-member Governing Body (GB) committee table under Institutional Governance per Registrar directive; updated deployment automation script (deploy.ps1). | 15
6 | 08-Jun-2026 to 11-Jun-2026 | Marketing Lead Security Infrastructure, Transport Timetable & Mechanical Faculty Roster | • Engineered custom lead safety guard utility npfThankYouGuard.js to protect /thank-you page against direct/fraudulent URL visits and guarantee genuine conversion tracking across all 5 inquiry touchpoints. • Created dedicated Thank-You layout and confirmation routing pipeline. • Digitized complete college bus route timetable and stop schedule per Transport coordinator circular following Principal's audit. • Collected, formatted, and updated Mechanical Engineering faculty roster, academic designations, and profiles per coordinator updates. | 16
7 | 13-Jun-2026 to 16-Jun-2026 | Teacher Guardian (TG) 134-Student Search System & Navigation Optimization | • Engineered interactive Mentor-Mentee (Teacher Guardian - TG) system mapping 134 students with real-time client-side search filtering. • Uploaded FRA Fee Proposal, New FRA, and Institute Level Fee structure documents; mapped AY 2026-27 Sem I Theory Timetable download spreadsheets. • Built Student Training WebP photo gallery with fullscreen lightbox view; embedded inline PDF viewers for MESA and Placement reports. • Removed obsolete 'Pay Fee' external link from header and mobile drawer per Senior Accountant mandate, routing payments strictly through college ERP. | 13.5
8 | 18-Jun-2026 to 21-Jun-2026 | MBA NBA Statements, E&TC Faculty Profiles & Laboratory Facilities Showcase | • Received approved NBA statements from MBA Dean (Dr. Archana Salve) via Director IT; integrated Vision and 4 Mission statements (M1–M4) into MBA Programme page using responsive styled card components. • Added profile data and portraits for E&TC faculty members (Prof. Sushma Patwardhan, Prof. Balu Tandale). • Addressed lab photo clarification queries with department coordinators and uploaded verified high-resolution E&TC laboratory facility images. | 9
9 | 22-Jun-2026 to 25-Jun-2026 | Mechanical Dept MESA Gallery, Faculty Onboarding & Autonomous Curricula | • Resolved restricted SharePoint folder access issue; collected, resized, and converted AY 2025-26 Semester II MESA activity photos to lightweight WebP. • Built and deployed updated MESA activities gallery and event report sections. • Onboarded newly joined faculty profile, qualifications, and portrait on Mechanical Department page. • Replaced curriculum structures with revised B.E. Mechanical (UG Autonomous Pattern) and M.Tech Heat Power Engineering (PG 2026-27 Pattern) documents. | 11.5
10 | 26-Jun-2026 to 30-Jun-2026 | Institutional Research Deep Overhaul (9-Task Revamp) & Audited Financials (NBA) | • Executed complete 9-task research overhaul requested by Dean R&D (Dr. Mahesh G. Bhong): - Updated 2025-26 research metrics (Scopus/WoS: 64, Peer Reviewed: 40, Books: 14, Patents: 23, Copyrights: 21) & configured 6-thumbnail card layout. - Added AY 2025-26 Indexed Journal Publications dataset; renamed Conference to Peer-reviewed and integrated publication dataset. - Added Book/Book Chapter 2025-26 table dataset; updated faculty seed funding allocation to ₹1,00,000/-. - Built Conferences Table: NCTAAI 4.0 (MCA), NTAI 2025 (Comp), NCDFTS-2026 (MBA), SDETM 2026 (Mech) with brochures and proceedings links. • Digitized, formatted, and published ICEM Audited Financial Statements & Balance Sheets for FY 2023-24 and FY 2024-25 for mandatory NBA accreditation disclosure. | 15
11 | 01-Jul-2026 to 05-Jul-2026 | SDETM Marquee Linking, Mechanical Intake & MBA Autonomous Curricula | • Integrated clickable scrolling marquee spotlight text 'INTERNATIONAL CONFERENCE (ICSDETM2026)' on Homepage linking directly to sdetm.indiraicem.ac.in. • Restructured Mechanical Engineering Programmes Offered tab with revised intakes: B.Tech Mech (60), M.Tech Heat Power (06), B.Tech Mech Working Professional (30). • Uploaded approved MBA Course Structure and Detailed Syllabus for AY 2026-27 under MBA Syllabus tab per Dr. Archana Salve's mandate for NBA compliance. • Added Vacation / Re-Exam Timetables (July 2026) and converted Navbar 'ERP Student' link to 'ERP Login' pointing to Edu Plus ERP. | 11
12 | 06-Jul-2026 to 09-Jul-2026 | Dedicated Bilingual FRA Fee Portal, UTM Marketing Engine & SDETM Deployment | • Developed dedicated /fra-fee-structure portal with English and Marathi official regulatory versions, desktop/mobile optimization, and homepage quick links. • Published 'FRA Fee Structure (A.Y. 2026-27)' PDF under FRA Fees tab across all department pages. • Engineered dynamic UTM query parameter forwarding (utm_source, utm_medium, utm_campaign, utm_content) into embedded NoPaperForms/Meritto iframes for 100% campaign attribution. • Executed AI&DS Department overhaul (+620 lines in FAQSectionAIDS.jsx) and deployed latest SDETM 2026 production build to cPanel hosting. | 16.5
13 | 15-Jul-2026 to 18-Jul-2026 | Strategic Plan (2026-2030) Dedicated Portal & Document Viewer Integration | • Received official mandate from Dr. Archana Salve via Director IT for NBA compliance. • Developed new dedicated Strategic Plan (2026-2030) page (/strategic-plan) with embedded PDF document viewer, zoom controls, and instant download button. • Integrated 'Strategic Plan' under About Us navigation dropdown across desktop and mobile menus. | 7
14 | 20-Jul-2026 to 25-Jul-2026 | MBA Department Comprehensive NBA Restructuring & Specialized Academic Tabs | • Handled major NBA restructuring: removed Integrated MBA tab and re-allocated faculty under MBA Course Staff tab per Dr. Archana Salve's request. • Extracted and processed standalone PNG portraits for Dr. Archana Salve and faculty members, resolving format incompatibilities. • Integrated institutional HR Leave Policy document in website Footer under Official Documents. • Converted raw MBA 2026-27 Syllabus Word documents into web-optimized, high-fidelity PDFs. • Created dedicated 'Newsletter' tab under MBA; engineered 3 specialized tabs ('Faculty Development Details', 'MBA Faculty Details', 'Teaching Cases'); updated Sanctioned Intake to 120 and Working Professional to 30. | 19.5
15 | 28-Jul-2026 to 31-Jul-2026 | MCA Admissions Launch & SDETM Portal Release Cycle | • Received latest official MCA Admission Brochure from Dr. Awantika Bijwe & Vijaykumar Saini; uploaded under MCA course page (/programs/mca/) with instant download action. • Pulled, compiled, and deployed updated SDETM 2026 conference portal codebase incorporating revisions from the SDETM committee meeting. • Validated server IP pointing, SSL certificates, propagation checks, and cross-browser responsiveness. | 6
16 | 04-Aug-2026 to 08-Aug-2026 | Computer Engineering NBA Formatting & Multi-Batch MCA/IMCA Curriculum | • Coordinated with Ms. Pragati Malusare on text layout styling; fine-tuned formatting across Computer Engineering Vision, Mission, POs, PSOs, and PEOs statements to apply clean justified alignment and dynamic responsive wrapping without modifying official text. • Structured MCA Syllabus tab into separate batches: MCA-(2024-26) Syllabus & MCA-(2025-27) Syllabus. • Added 5-year Integrated MCA Course Structure (2025-2030) PDF on IMCA page; optimized and deployed assets. | 9.5
17 | 10-Aug-2026 to 14-Aug-2026 | Creation of Dedicated Admission 2026 Portal, NBA DCS Report & Cyber Privacy Audit | • Received high-priority mandate from Registrar & Director IT; created new dedicated top-level 'Admission 2026' portal (/admission-2026) with programme-wise folder categories: Engineering, MBA, MCA, DSE (Lateral Entry), and Working Professionals. • Coordinated cyber safety & privacy policy with Dr. Awantika Bijwe, Prakash Bhusari, and Principal Dr. Nilesh Uke; removed faculty Date of Birth (DOB) fields across all departmental staff profiles for cybersecurity compliance. • Created new dedicated NBA tab placed above NAAC under About Us > Accreditation (/about/accreditation/) and uploaded official Mechanical DCS Report PDF. • Updated M.Tech Mechanical Engineering page heading to reflect official nomenclature: 'Specializing in Heat Power Engineering'; updated MCA and MBA staff rosters. | 19.5
18 | 17-Aug-2026 to 21-Aug-2026 | MCA 3-Tier Academic Architecture, Statutory Eligibility & IT Faculty Updates | • Updated MCA Syllabus & Course Structure into 3 distinct tabs: MCA-(2026-28) Syllabus, MCA-(2025-27) Modified Syllabus, and MCA-(2024-26) Course Pattern. • Updated Sanctioned Intake to 120 Seats and added full statutory eligibility criteria for Maharashtra State, All India, J&K, NRI/OCI, and Lateral Entry candidatures. • Updated IT Department faculty experience and research datasets per HOD directive; standardized Dr. Prashant Sunil Borde profile under MBA faculty. | 10.5
19 | 22-Aug-2026 to 28-Aug-2026 | First Year Engineering (FYE) Overhaul, Institutional R&D Policies & E&TC Syllabi | • FYE Page update requested by Ms. Trupti Kathale: added FY B.Tech 2026 Pattern Syllabus, updated Board of Studies (BOS) 26-member committee, and onboarded 4 new faculty profiles (Mr. Yadnyesh Khotre, Mr. Himanshu Tarale, Mr. Dipak Sabale, Ms. Preeti Katyal). • Uploaded institutional Research Policies for 2024-25, 2025-26, and 2026-27 under /research/ requested by Dean R&D (Dr. Mahesh Bhong). • E&TC Department overhaul: resolved conflicting Word draft changes, added faculty profiles/photos for Prof. Sushma Patwardhan and Prof. Balu Tandale, updated syllabus files, and deployed live with confirmation from Prof. Priyanka Patil. | 13
20 | 01-Sep-2026 to 05-Sep-2026 | Campus Life Committees Revamp, SIH 2026 Banner & Site-Wide WebP Optimization | • Major Campus Life Committees Page revamp (+1098 lines): uploaded and integrated official signed PDFs for all 15+ Non-Statutory Committees and 8+ Statutory Committees. • Designed, cropped, resized, and deployed Smart India Hackathon 2026 banner requested by Mrs. Anita Patil (Asst Prof Comp) to the homepage rotational hero slider for desktop and mobile. • Executed site-wide WebP compression across 50+ institutional gallery images and documents. | 14
21 | 06-Sep-2026 to 09-Sep-2026 | Against-CAP (ACAP) & IL Vacancy Portals, Regulatory FRA Notices & Admission Hotline | • Added official institutional banner slider on Homepage with responsive desktop (si_icem_desk.webp) and mobile (si_icem_mob.webp) artwork, linking directly to FRA Fee Structure. • Added Institute Level (IL) Admission Fee Structure 2026-27 and regulatory FRA notice download links on /fees page. • Integrated official Against-CAP / Institute Level Vacancy Position PDFs for B.Tech First Year (FE), Direct Second Year (DSE), MBA, and MCA with compact mobile-friendly table cards, quick-action view/download buttons, and urgent admission hotline banners. • Updated provisional merit lists notice and reporting schedules on /admission-2026. | 14.5
Total Billable Hours (21 Consolidated Production Sprints)